## RISK TABLE
Risk ID | Risk source | Asset | Asset owner | Threat | Consequence | Raw probability | Raw impact | Raw risk rating | Vulnerability | Treatment | Status | Treated probability | Treated impact | Current risk rating | Target risk rating | Plan | Deadline | Risk scenario
1.1 | Insider (malicious) | SELECT ASSETS |  | Manipulation of Hardware or Software |  | 2 | 5 | 35 | Lack of change control procedure | Change management | Open | 1 | 3 | 12 |  |  | 2017-12-31
1.2 | Insider (malicious) | SELECT ASSETS |  | Theft of Devices, Storage Media and Documents |  | 2 | 2 | 8 | Lack of audit trail | Inventory of assets | Open | 2 | 1 | 3 |  |  | 2017-12-31
2.1 | Insider (accidential) | SELECT ASSETS |  | Disclosure of internal documents | Data leak | 3 | 2 | 10 | Insufficient security training | Information security awareness, education and training | Open | 2 | 1 | 3 |  |  | 2017-12-31 | Due to (spear) phishing
2.2 | Insider (accidential) | SELECT ASSETS |  | Malware infection |  | 4 | 3 | 21 | Lack of e-mail usage policy | Policies for information security | Open | 2 | 1 | 3 |  |  | 2017-12-31 | Via e-mail, social media, chat, web or removable storage device
2.3 | Insider (accidential or malicious) | SELECT ASSETS |  | Unauthorised Access to IT Systems |  | 2 | 4 | 24 | Inadequate network management (resilience of routing) | Access to networks and network services | Open | 1 | 3 | 12 |  |  | 2017-12-31 | 3G/4G sticks
2.4 | Insider (accidential) | SELECT ASSETS |  | Reusing passwords | Unauthorized access to ESS systems | 1 | 4 | 20 | Unprotected password tables | Password management system | Open | 1 | 2 | 6 |  |  | 2017-12-31 | A third party is compromised
2.5 | Insider (accidential) | SELECT ASSETS |  | Using private e-mail or cloud storage solutions | Disclosure of internal data | 3 | 3 | 18 | Unprotected public network connections | Security of equipment and assets off-premises | Open | 2 | 2 | 8 |  |  | 2017-12-31 | Private account or service provider is compromised
2.6 | Insider (accidential) | SELECT ASSETS |  | Malfunction of Devices or Systems |  | 4 | 2 | 12 | Incorrect use of software and hardware | Information security awareness, education and training | Open | 3 | 1 | 4 |  |  | 2017-12-31
2.7 | Insider (accidential) | SELECT ASSETS |  | Disclosure of Sensitive Information |  | 3 | 4 | 28 | Lack or insufficient 'clear desk and clear screen' policy | Clear desk and clear screen policy | Open | 1 | 4 | 20 |  |  | 2017-12-31
3.1 | Supplier | SELECT ASSETS |  | Malfunction of Devices or Systems |  | 2 | 4 | 24 | No or insufficient software testing | System security testing | Open | 1 | 3 | 12 |  |  | 2017-12-31
3.2 | Supplier | SELECT ASSETS |  | Software Vulnerabilities or Errors |  | 3 | 3 | 18 | Well-known flaws in the software | System acceptance testing | Open | 2 | 2 | 8 |  |  | 2017-12-31
3.3 | Supplier (accidental) | SELECT ASSETS |  | Failure or Disruption of the Power Supply | Power loss | 2 | 4 | 24 | Unstable power grid | Protecting against external and environmental threats | Open | 1 | 3 | 12 |  |  | 2017-12-31
4.1 | Client | SELECT ASSETS |  | Manipulation of Information |  | 2 | 2 | 8 | Wrong allocation of access rights | User access provisioning | Open | 1 | 2 | 6 |  |  | 2017-12-31
4.2 | Client | SELECT ASSETS |  | Unauthorised Access to IT Systems |  | 2 | 3 | 15 | Poor password management | Password management system | Open | 1 | 3 | 12 |  |  | 2017-12-31
4.3 | Clent (accidental) | SELECT ASSETS |  | Attack |  | 4 | 2 | 12 | Lack of formal policy on mobile computer usage | Acceptable use of assets | Open | 3 | 1 | 4 |  |  | 2017-12-31 | BYOD
5.1 | Competitor | SELECT ASSETS |  | Malicious Software |  | 1 | 5 | 30 | Lack of change control procedure | Change management | Open | 1 | 4 | 20 |  |  | 2017-12-31
5.2 | Competitor | SELECT ASSETS |  | Software Vulnerabilities or Errors |  | 3 | 3 | 18 | No or insufficient software testing | Management of technical vulnerabilities | Open | 2 | 3 | 15 |  |  | 2017-12-31
6.1 | Terrorist | SELECT ASSETS |  | Attack |  | 2 | 5 | 35 | Single point of failure | Response to information security incidents | Open | 2 | 2 | 8 |  |  | 2017-12-31
6.2 | Terrorist | SELECT ASSETS |  | Failure or Disruption of the Power Supply |  | 2 | 4 | 24 | Lack or insufficient Service Level Agreement | Security of equipment and assets off-premises | Open | 2 | 3 | 15 |  |  | 2017-12-31
7.1 | Criminal | SELECT ASSETS |  | Unauthorised Use or Administration of Devices and Systems |  | 4 | 5 | 45 | Lack of fault reports recorded in administrator and operator logs | Administrator and operator logs | Open | 3 | 4 | 28 |  |  | 2017-12-31
7.2 | Criminal | SELECT ASSETS |  | Identity Theft |  | 4 | 4 | 32 | Lack of formal process for access right review (supervision) | Working in secure areas | Open | 3 | 3 | 18 |  |  | 2017-12-31
8.1 | Activist (or hactivist) | SELECT ASSETS |  | Unauthorised Access to IT Systems |  | 3 | 5 | 40 | Lack of formal procedure for user registration and de-registration | User registration and de-registration | Open | 2 | 3 | 15 |  |  | 2017-12-31
8.2 | Activist (or hactivist) | SELECT ASSETS |  | Denial of Service |  | 1 | 3 | 12 | Lack of monitoring mechanisms | Planning information security continuity | Open | 1 | 2 | 6 |  |  | 2017-12-31
9.1 | State (sponsored sabotage) | SELECT ASSETS |  | Sabotage |  | 2 | 4 | 24 | Lack of procedures for classified information handling | Classification of information | Open | 2 | 3 | 15 |  |  | 2017-12-31
9.2 | State (sponsored sabotage) | SELECT ASSETS |  | Eavesdropping |  | 3 | 3 | 18 | Lack of information processing facilities authorization | Screening | Open | 2 | 3 | 15 |  |  | 2017-12-31
10.1 | Force majeure | SELECT ASSETS |  | Destruction of Devices or Storage Media |  | 1 | 4 | 20 | Lack of physical protection of the building, doors and windows | Securing offices, rooms and facilities | Open | 1 | 2 | 6 |  |  | 2017-12-31
10.2 | Force majeure | SELECT ASSETS |  | Fire |  | 1 | 5 | 30 | Lack of physical protection of the building, doors and windows | Protecting against external and environmental threats | Open | 1 | 3 | 12 |  |  | 2017-12-31

## Guidance
Column | Notes
ID | Assign a unique reference in order to be able to identify each risk unambiguously.
Risk | Describe the cyber security risk briefly so that people will understand what risk you are assessing.
Asset | Asset is any data, device, or other component of the environment that supports information-related activities.
Asset owner | Who is the Information asset owner, the person who will be held to account if the risk treatments are inadequate, incidents occur and the organization is adversely impacted?
Threat | A potential cause of an incident, that may result in harm of systems and organization.
Consequence | Describe the potential impacts should the risk occur, ideally in business terms. Decide whether to use "worst case" or "anticipated" impacts and be consistent about it.
Raw probability | Enter the probability or likelihood that the risk would occur if it was totally untreated, as a percentage value.
Raw impact | Enter the potential business impact if the risk occurred without any treatment, as a percentage value.
Raw risk rating | This is the product of the raw probability and impact values, in other words the raw/untreated/inherent level of risk.
Vulnerability | A weakness of an asset or group of assets that can be exploited by one or more threats.
Treatment | Describe how the risk is to be treated. Note that controls are just one option: risks can also be avoided, transferred or accepted.
Status | To what extent is the planned treatment in place? "Planned" means the treatment is only a plan at present - nothing has been done about it as yet. "Unfinished" means that decisions are made but treatment is not operational. "Finished" means the treatment is fully operational.
Treated probability | Enter the probability that the risk will eventuate once the treatment is fully in effect, in the same way as for before mitigation.
Treated impact | Enter the likely impact once the treatment is fully in effect, in the same way as before mitigation.
Current risk rating | This is the risk rating today, given the implementation status and anticipated probability and impact values when fully completed. For example, if the raw risk value is 50% and the treated risk value is 30% but the treatment is only 50% implemented, the current risk level is 40%. In reality, many security controls are either fully implemented and fully effective, or partially implemented and not at all effective - but the risk calculation here takes into account the fact that work is under way, hence management can assume it will be treated in due course.
Target risk rating | This is the product of the anticipated probability and impact values once the risk treatment is fully implemented. In other terms, it may considered as "acceptable level of risk".
Plan | What is the plan to develop and implement risk treatment options?
Deadline | Record the date on which the security measures should be implemented by plan.
Risk scenario description | Risk scenario is characterized by a threat actor (e.g. internal, external), a threat type (e.g. malicious, accidential, failure, natural), event (e.g. disclosure, modification, theft, destruction), asset or resource (e.g. people, process, infrastructure, information), time (e.g. duration, timing of occurrence, detect and react).

## Asset list
SELECT ASSETS | Description | Confidentiality need | Integrity need | Availability need

## Asset owners
Asset | Owner name | Position | Ownership confirmation

## Threats list
SELECT THREAT
Fire
Unfavourable Climatic Conditions
Water
Pollution, Dust, Corrosion
Natural Disasters
Environmental Disasters
Major Events in the Environment
Failure or Disruption of the Power Supply
Failure or Disruption of Communication Networks
Failure or Disruption of Mains Supply
Failure or Disruption of Service Providers
Interfering Radiation
Intercepting Compromising Emissions
Interception of Information / Espionage
Eavesdropping
Theft of Devices, Storage Media and Documents
Loss of Devices, Storage Media and Documents
Bad Planning or Lack of Adaption
Disclosure of Sensitive Information
Information or Products from an Unreliable Source
Manipulation of Hardware or Software
Manipulation of Information
Unauthorised Access to IT Systems
Destruction of Devices or Storage Media
Failure of Devices or Systems
Malfunction of Devices or Systems
Lack of Resources
Software Vulnerabilities or Errors
Violation of Laws or Regulations
Unauthorised Use or Administration of Devices and Systems
Incorrect Use or Administration of Devices and Systems
Abuse of Authorisations
Absence of Personnel
Attack
Coercion, Extortion or Corruption
Identity Theft
Reputation of Actions
Abuse of Personal Data
Malicious Software
Denial of Service
Sabotage
Social Engineering
Replaying Messages
Unauthorised Entry to Premises
Data Loss
Loss of Integrity of Sensitive Information
Disclosure of internal documents
Malware infection
Reusing passwords
Using private e-mail or cloud storage solutions

## Vulnerability list
SELECT VULNERABILITY
Insufficient maintenance/faulty installation of storage media
Lack of periodic replacement schemes
Susceptibility to humidity, dust, soiling
Sensitivity to electromagnetic radiation
Lack of efficient configuration change control
Susceptibility to voltage variations
Susceptibility to temperature variations
Unprotected storage
Lack of care at disposal
Uncontrolled copying
No or insufficient software testing
Well-known flaws in the software
No 'logout' when leaving the workstation
Disposal or reuse of storage media without proper erasure
Lack of audit trail
Wrong allocation of access rights
Widely-distributed software
Applying application programs to the wrong data in terms of time
Complicated user interface
Lack of documentation
Incorrect parameter set up
Incorrect dates
Lack of identification and authentication mechanisms like user authentication
Unprotected password tables
Poor password management
Unnecessary services enabled
Immature or new software
Unclear or incomplete specifications for developers
Lack of effective change control
Uncontrolled downloading and use of software
Lack of back-up copies
Lack of physical protection of the building, doors and windows
Failure to produce management reports
Lack of proof of sending or receiving a message
Unprotected communication lines
Unprotected sensitive traffic
Poor joint cabling
Single point of failure
Lack of identification and authentication of sender and receiver
Insecure network architecture
Transfer of passwords in clear
Inadequate network management (resilience of routing)
Unprotected public network connections
Absence of personnel
Inadequate recruitment procedures
Insufficient security training
Incorrect use of software and hardware
Lack of security awareness
Lack of monitoring mechanisms
Unsupervised work by outside or cleaning staff
Lack of policies for the correct use of telecommunications media and messaging
Inadequate or careless use of physical access control to buildings and rooms
Location in an area susceptible to flood
Unstable power grid
Lack of physical protection of the building, doors and windows
Lack of formal procedure for user registration and de-registration
Lack of formal process for access right review (supervision)
Lack or insufficient provisions (concerning security) in contracts with customers and/or third parties
Lack of procedure of monitoring of information processing facilities
Lack of regular audits (supervision)
Lack of procedures of risk identification and assessment
Lack of fault reports recorded in administrator and operator logs
Inadequate service maintenance response
Lack or insufficient Service Level Agreement
Lack of change control procedure
Lack of formal procedure for ISMS documentation control
Lack of formal procedure for ISMS record supervision
Lack of formal process for authorization of public available information
Lack of proper allocation of information security responsibilities
Lack of continuity plans
Lack of e-mail usage policy
Lack of procedures for introducing software into operational systems
Lack of records in administrator and operator logs
Lack of procedures for classified information handling
Lack of information security responsibilities in job descriptions
Lack or insufficient provisions (concerning information security) in contracts with employees
Lack of defined disciplinary process in case of information security incident
Lack of formal policy on mobile computer usage
Lack of control of off-premise assets
Lack or insufficient 'clear desk and clear screen' policy
Lack of information processing facilities authorization
Lack of established monitooring mechanisms for security breaches
Lack of regular management reviews
Lack of procedures for reporting security weaknesses
Lack of procedures of provisions compliance with intellectual rights

## Treatment list
SELECT TREATMENT
Policies for information security
Review of the policies for information security
Information security roles and responsibilities
Segregation of duties
Contact with authorities
Contact with special interest groups
Information security in project management
Mobile device policy
Teleworking
Screening
Terms and conditions of employment
Management responsibilities
Information security awareness, education and training
Disciplinary process
Termination or change of employment responsibilities
Inventory of assets
Ownership of assets
Acceptable use of assets
Return of assets
Classification of information
Labelling of information
Handling of assets
Management of removable media
Disposal of media
Physical media transfer
Access control policy
Access to networks and network services
User registration and de-registration
User access provisioning
Management of privileged access rights
Management of secret authentication information of users
Review of user access rights
Removal or adjustment of access rights
Use of secret authentication information
Information access restriction
Secure log-on procedures
Password management system
Use of privileged utility programs
Access control to program source code
Policy on the use of cryptographic controls
Key management
Physical security perimeter
Physical entry controls
Securing offices, rooms and facilities
Protecting against external and environmental threats
Working in secure areas
Delivery and loading areas
Equipment siting and protection
Supporting utilities
Cabling security
Equipment maintenance
Removal of assets
Security of equipment and assets off-premises
Secure disposal or reuse of equipment
Unattended user equipment
Clear desk and clear screen policy
Documented operating procedures
Change management
Capacity management
Separation of development, testing and operational environments
Controls against malware
Information backup
Event logging
Protection of log information
Administrator and operator logs
Clock synchronisation
Installation of software on operational systems
Management of technical vulnerabilities
Restrictions on software installation
Information systems audit controls
Network controls
Security of network services
Segregation in networks
Information transfer policies and procedures
Agreements on information transfer
Electronic messaging
Confidentiality or nondisclosure agreements
Information security requirements analysis and specification
Securing application services on public networks
Protecting application services transactions
Secure development policy
System change control procedures
Technical review of applications after operating platform changes
Restrictions on changes to software packages
Secure system engineering principles
Secure Development Environment
Outsourced development
System security testing
System acceptance testing
Protection of test data
Information security policy for supplier relationships
Addressing security within supplier agreements
ICT supply chain
Monitoring and review of supplier services
Managing changes to supplier services
Responsibilities and procedures
Reporting information security events
Reporting information security weaknesses
Assessment of and decision on information security events
Response to information security incidents
Learning from information security incidents
Collection of evidence
Planning information security continuity
Implementing information security continuity
Verify, review and evaluate information security continuity
Availability of information processing facilities
Identification of applicable legislation and contractual requirements
Intellectual property rights
Protection of records
Privacy and protection of personally identifiable information
Regulation of cryptographic controls
Independent review of information security
Compliance with security policies and standards
Technical compliance review

## Impact scale
Business impact
| Extreme | Major | Moderate | Minor | Insignificant
Manufacturing outage (days) | > 7 | < 7 > 2 | > 2 | < 2 > 1 | < 1
Cost (MEUR) | > 500 | < 500 > 100 | > 100 | < 100 > 5 | < 5
Legal | Criminal offense | Violation of regulations | Violation of contracts | Minor legal violations | None
Public confidence | Loss of license to operate | Loss of brand image | Loss of customer confidence | Negative media attention | None
People on-site | Fatality | Major injury | Permanent injury | Minor injury | Possible first aid
People off-site | Fatality or major community incident | Major injury | Permanent injury or community impact | Minor injury | No complaints
Environmental safety | Citation by regional or national agency or long-term segnificant damage over large area | Citation by national agency | Citation by local agency | Release above reportable limits | Small, contained release below reportable limits
Infrastructure and services | Impacts multiple business sectors or disrupts community services in a major way | Impacts few business sectors or disrupts community services | Potential to impact a business sector at a level beyond that of a single company. Potential to impact services of a community | Minor impact limited to individual company. Minor impact on community services | Little to no impact to business sectors beyond the individual company. Little to no impact on community services
| 100% | 80% | 62% | 25% | 1%

## Probability scale
Probability | (Almost) certain | We are bound to experience further incidents of this nature - in fact they are probably occuring right now! | 100%
| Probable | We are likely to experience incidents of this nature before long | 80%
| Possible | It is distinctly possible that we will experience incidents of this nature | 62%
| Unlikely | Incidents of this nature are uncommon but there is a genuine chance that we may experience them at some future point | 25%
| Rare | Although they are conceivable, we will probably never experience incidents of this nature | 1%

## Risk matrix
| 5 | 4 | 3 | 2 | 1
5 | 50 | 36 | 24 | 14 | 6 | Probability ---------------------->
4 | 45 | 32 | 21 | 12 | 5
3 | 40 | 28 | 18 | 10 | 4
2 | 35 | 24 | 15 | 8 | 3
1 | 30 | 20 | 12 | 6 | 2
< --------------------------------------- Impact
Risk = Impact*Probability+Impact*Impact